## Sheet1
Spector City
Development Schedule
TASK NAME | ASSIGNED TO | START DATE | DUE DATE | DURATION | % DONE | SPRINT/MILESTONE
Brain Storming Ideas | All member | 2019-09-19 | 2019-09-26 | 7 | 100% | Designing
Filtering game ideas | All member | 2019-09-26 | 2019-10-10 | 14 | 100% | Designing
Defining Constrains and Requirement | All member | 2019-10-10 | 2019-10-17 | 7 | 100% | Designing
Feasibility study | All member | 2019-10-17 | 2019-10-24 | 7 | 100% | Designing
Start writing Initial Report | Lam Wang Yu/ Wu Man Kit | 2019-10-24 | 2019-11-17 | 24 | 100% | Documentation
Start developing first prototype | ZhangYao Hui/Chan Chiu Shun | 2019-10-24 | 2019-11-21 | 28 | 100% | Prototyping
Finalizing Initial Report | All member | 2019-11-17 | 2019-12-08 | 21 | 100% | Prototyping
Drawing diagrams (UML) | Lam Wang Yu | 2019-12-19 | 2020-01-09 | 21 |  | Prototyping
Writing Interm Report | Lam Wang Yu/ Wu Man Kit | 2019-12-26 | 2020-01-09 | 14 |  | Documentation
Implementing level 1 | ZhangYao Hui/Chan Chiu Shun | 2020-01-09 | 2020-02-27 | 49 |  | Implementation
Drawing game art | Lam Wang Yu/ Wu Man Kit/ Chan Chiu Shun | 2020-01-09 | 2020-02-20 | 42 |  | Implementation
Implementing game menu | ZhangYao Hui/Chan Chiu Shun | 2020-02-06 | 2020-02-27 | 21 |  | Implementation
Small testing on level 1 | All member | 2020-02-20 | 2020-02-27 | 7 |  | Testing
Implementing level 2 | ZhangYao Hui/Chan Chiu Shun | 2020-03-05 | 2020-04-02 | 28 |  | Implementation
Implementing level 3 | ZhangYao Hui/Chan Chiu Shun | 2020-04-02 | 2020-04-30 | 28 |  | Implementation
Developing Test Plan | Lam Wang Yu | 2020-04-02 | 2020-04-19 | 17 |  | Testing
Testing and finetuning | All member | 2020-04-19 | 2020-05-19 | 30 |  | Testing
Writing Final Report | Lam Wang Yu/ Wu Man Kit | 2020-04-09 | 2020-05-20 | 41 |  | Documentation
Group member
Lam Wang Yu
Wu Man Kit
ZhangYao Hui
Chan Chiu Shun
Formulas:
DUE DATE = [START DATE]+14